## CeC Project Plan
Community e-Connect Implementation Process and Milestones - template
Insert partners and intervention type
CeC Implementation Process, Resource Requirements and Timeline
Target Date | Completed? | Task / Meeting / Milestone | Purpose | Status Notes
|  | Introductory / Kick-Off CeC Call with key stakeholders of partnership | - bring together collaborating partners - provide a high level overview of the project - obtain shared commitment to goals and project approach - discuss next steps and partner to-do's
Schedule call with screen-sharing
Draft presentation
|  | Legal Agreements | - establish a data-sharing MOU between the clinical and community partners
NACDD share example agreements
Partners send to respective legal teams for review
Both partners sign agreement
|  | Trusted Agent Process | - MedAllies is Bowlink's HISP, which enables the processing of referral info - documents describe CBO responsibilities as part of the referral and feedback process - required to meet national interoperability standards
Bowlink leads a call with CBO contacts to explain process and share TA Addendum (organization level) and TA Agreement (staff level)
CBO contact secures appropriate signatures, completing I-9 reqs
Bowlink and MedAllies confirm CBO trusted agent status
|  | Workflow Meetings and Data Element Confirmation | - determine CeC workflow in detail, using examples provided by NACDD as starting points - document the workflow / process within each partner, for each referral type - review data element template and info to be exchanged
NACDD share workflow toolkit and examples, debriefing with each partner as appropriate
Partners modify examples to match their intended workflow
NACDD facilitates a mtg to combine partner workflows, determining feedback report frequency and triggers
During WF mtg, review and finalize data elements
|  | IT Assessment | - review existing and planned IT capabilities - document the technical integration requirements - IT will review workflow and data element requests to ensure alignment with the capabilities of the integrated systems
NACDD facilitates a mtg with clinical partner technical leads to review process
Clinical partner reaches out to EMR vendor
Hold call with EMR vendor to plan for integration - determine if have a STAGE enivronment for testing or go straight to PROD
|  | Technical Integration | Series of meetings to: - review EMR, eReferral system and other system integration requirements - develop integration plan across systems - perform all required hardware/software installations, software enhancements, technical configuration work and QA testing
Bowlink work with IT teams and EMR vendor in test environment
Bowlink developed custom eRG system for CBO
|  | Training | - ensure clinical users receive training and understand any changes in workflow as well as modifications to their EMR system - provide eRG training to CBO users
NACDD revise eRG training materials as needed
NACDD provide training to eRG users, including testing
NACDD / Bowlink work with EMR vendor to ensure clinical users are trained on the system enhancements
|  | Implementation Go Live | - meet all installation, configuration and testing requirements - validate operation and performance - test, monitor and evaluate referral / feedback processing as required to confirm ongoing operation as well as capacity for monitoring and evaluation
Partners begin sending patient referrals
NACDD monitors progress biweekly, providing updates and meeting with partners as appropriate

## Kick off Highlevel Timeline (hidden)
[Insert Parthership name]
Goal: establish an e-Referral connection from [Clincal site] to [CBO] for [Intervention] among patients with [Health Condition]. The referral will initiate in [Clinical site's EMR], and be received by [CBO] via the e-Referral Gateway (eRG). Feedback will also be sent directly to [Clinical site's EMR] from [CBO] via the eRG.
PWTF e-Referral Implementation Process and Timeline
√ | Meeting / Task Completion Date | Meeting / Task Name | Purpose | Talking Points / Materials | Action Items | Mode | Attendees | Lead | Notes
|  | Introductory e-Referral Call | Confirm / Define condition, intervention, and partners Provide high level e-Referral overview Answer prelim grantee questions | eRG description Legal agreement Current workflows Data element template Timeline Reporting / evaluation expectations | DPH to send organization documents for grantee completion Provide eMedApps / MLCHC contact if appropriate DPH to send meeting minutes | Phone 30 mins | DPH, Partnership (CBO & HCP) | SS
Complete Memorundum of Understang (MOU) - CHC>CBO
Complete e-Referral Agreement (general overview doc for intra-partnership use)
Complete Organization Documents
Submit Current Workflow
|  | Kick off Meeting with eRG demonstration | Orient involved partners to e-Referral process Begin workflow and DE discussion Answer basic IT questions Provide basic eRG overview | Checklist and Orientation Presentation Timeline | Send technical specs to clin IT, who should reach out to EMR vendor Send DE template to grantee Schedule workflow and DE meeting DPH to send meeting minutes | In-Person 2 hr | DPH, Partnership (CBO & HCP) | JP / SS
Schedule weekly IT meetings
|  | Workflow and Data Element Meeting **Ensure appropriate end-users are able to attend meeting - will not move forward without CBO, Clinical end-users and IT | Define workflows around all e-Referral steps Discuss data elements | Current referral workflows and/or draft e-Referral workflows Data element template Be prepared to give eRG demo / refresher as needed | Revise workflows and submit to DPH or DPH send to grantee Revise DE template and submit to DPH or DPH send to grantee DPH to send meeting minutes | In-Person 2 hr | DPH, Partnership (CBO & HCP Workflow/IT Team) | JP, Jen Kincaid from MLCHC
Clinical outgoing referral
CBO receiving and acting on referral
CBO sending feedback
Clinical site receiving and acting on feedback
Data elements
Solicit workflow draft feedback from DPH SMEs
Revised drafts reviewed internally by workflow group and SMEs, as appropriate, and sent back to grantees
Schedule conference call / webinar to finalize with grantees, as needed
|  | IT Assessment | Review technical capabilities of HCP EMR system and eReferral system Develop technical plan for integration between the systems. | EMR system / version being used Current interoperability capabilities Interoperability options for e-Referral Referral and feedback report message types Referral and feedback report data element content Project plan overview Provide an eRG overview if not done previously | Assess functionality and upcoming issues Discuss integration technical options Document first draft technical project plan DPH to send meeting minutes | Phone / webinar 60 - 90 mins; will require multiple sessions | DPH IT and CHC IT teams | MS, JP
Create custom eRG test environment
Determine eReferral interoperability format (eRG, SFTP, Batch upload/download, Web services/API, Mass HiWay SMIME/LAND/XDR-SOAP)
Determine preferred referral and feedback report message type (CCD, CCR, HL7, custom)
Develop preliminary technical project plan for EMR/eReferal system integration.
Address any issues that came up during assessment
|  | Present eRG and Train SuperUsers | Obtain commitment/approval from clinical site and CBO staff that referral types, referral content and workflow is acceptable. | Custom eRG configuration Confirm referral types Confirm message content (referral and feedback reports) Confirm workflow Confirm referral statuses Confirm activity statuses | Document Clinical and CBO feedback Adjust eRG confiugurations based on grantee feedback as appropriate Review any modifications with HCP/CBO Obtain sign off |  | DPH | JP
|  | Test functionality with CBO, reviewing intervention-specific data elements - line by line review |  | DPH act as clinical site with CBO; DPH act as CBO with clinical site if both are testing | Adjust based on feedback from CBO and clinical site
Review eRG configuration, data elements with clinical site
Feedback submitted to DPH
Reconfigure and Re-test as needed
CBO formally approve / sign off on eRG configuration
|  | Technical Integration Implementation | ▪ Perform and document backend tasks facilitaing the integration of the functional workflow including defined Data Elements into the eMR and Testing the system configurations |  | ▪ Finalize Technical Project plan ▪ Schedule recurring technical meeting ▪ Document technical Spec ▪ Document eMR User Interface screenshots |  | DPH IT and CHC IT teams | JP
Finalize Technical Project Plan
Formalize recurring meeting schedule (typically weekly)
Perform EMR enhancements - review data proposed elements to determine how to extract the data fields
Configure 3rd party interface tools (Mass HiWay, eMedApps, others?)
Complete EMR / eRG configuration
Test functionality from EMR to eRG and vice versa
Clinical site and CBO formally approve configuration
|  | User eRG Training | ▪ Ensure that clinical users receive training and understand the eMR enhancements ▪ Provide eRG training to CBO user who will be using the receiving the e-Referrals | ▪ CBO User set up form ▪ eMR eReferral user interface Training document ▪ eRG Training document | ▪ Confirm completion that user set up form is completed ▪ Set up CBO user in eRG test system ▪ Prepare/Gather user training documents ▪ Perform CHC and CBO User training | In person or webinar, 60 mins | DPH | AB
Complete ALL User Training (at clinical site, could be internal training with DPH / MLCHC support)
|  | GO LIVE- Move Code to Production | Move code to Production |  | ▪ Activate production environment to provide the ability to sending referrals | N/A | DPH and Partnership (CBO & CHC) | MS, JP
Confirm Code Move
Go Live
|  | Hand-off; Progress Monitoring & Evaluation (Over Time)- DPH | ▪ Ensure user engagement and referral volume ▪ Provide and user support as needed |  | ▪ Provide daily referral and feedback report counts accordingly | N/A | DPH Monitoring and Evaluations team
Handoff Meeting/email
Document Lessons Learned

## Tech Project Plan (Sample)
Technical Project Plan
Action Items
•Detrmine eReferrral interoperability format such as SFTP
•Determine implementation options and timeline to add fields required to support the workflow – Determine preferred referral and feedback report message type (CCD, CCR, HL7, custom) – Review the proposed data elements to determine how to extract the data fields and create the referral message (e.g. CCD, HL7 2.x, XML, etc.)
Technical Requirements Gathering | Proposed Date | Actual Date
Signed proposal and SLA to begin work
Configure test environment with eRG - eRG configuration
Conduct eRG - eRG workflow review
Verify data elements captured in eMR
Submit proposal to eMR vendor and contract
eMR Vendor completes enhancements
Review and Approval of Referral and Feedback Report Message Format
Technical Requirements Complete
EMR to eReferral System Integration
Install/Enable Interoperability Interfaces as required
Build complete (Send/receive message to /from eReferral System and auto update referral in eMR)
Configure Test eMR eReferral system interface
Testing
Changes
Test Changes
Integration Complete
Pre-Production testing
Initiate Pre-Production Testing with Provider and eReferral
Complete Pre-Production Testing
Provide training
System live in production
Post production monitoring
Project Complete

## Sheet5 (hidden)
Technical Project Plan
Action Items
•LAND implementation follow up
•Determine implementation options and timeline to add fields required to support the workflow – Determine preferred referral and feedback report message type (CCD, CCR, HL7, custom) – Review the proposed data elements to determine how to extract the data fields and create the CCD document or HL7 message
•Manage project plan
•Determine Server needs to support Interface Exchange server
•Install and configure Inteface Exchange server
•Generate sample CCD referral and HL7 feedback report
•Configure eReferral system for Partnership's Intervention referral and feedback reports.
Technical Requirements Gathering | Proposed Date | Actual Date
Signed proposal and SLA to begin work
Complete referral workflow
Complete data element template
Configure test environment with eRG - eRG configuration
Conduct eRG - eRG workflow review
Verify data elements captured in eMR
Submit proposal to eMR vendor and contract
eMR Vendor completes enhancements
Review and Approval of CCDA & Template
Technical Requirements Complete
EMR to eReferral Gateway Integration (Thirdparty e.g e-Medapps)
Install Interface Exchange Server and Provide Access
Installation of Exchange Interface
Build complete (Send/receive message to /from Gateway and auto update referral in eMR
Configure Test eMR eReferral system interface
Testing
Changes
Test Changes
Integration Complete
EOHHS and CHC Pre-Production testing
Initiate Pre-Production Testing with EOHHS
Complete Pre-Production Testing with EOHHS
Provide training
System live in production
Post production monitoring
Project Complete